Homeschool Consulting Business

2-Week Launch Plan

This document has two parts: 1. A day-by-day action plan for the business owners (your parents) to follow. 2. A website specification section — everything the web developer needs to build the site.

| The Offer Free: 15-min Discovery Call Paid: 25-min Video Consultation — $50 | Goal by Day 14 3 paid clients booked + website live |
| --- | --- |

# PART 1: THE BUSINESS ACTION PLAN

This section is for the business owners. Follow each day in order. Do not skip ahead — the steps build on each other.

## WEEK 1 — Build the Foundation (Days 1–7)

Your only job this week is to get everything set up. Do not try to get clients yet. Focus on building the tools so when you reach out, you look professional.

DAY 1 — Define Your Business Identity

What to do:

- Write your "I help" statement. Fill in this template:

"I help [type of mom] who [problem they have] to [result you give them]."

Example: "I help new homeschool moms who feel overwhelmed and don't know where to start to build a simple, effective homeschool routine their kids actually enjoy."

- Write a short bio (3–4 sentences): Who you are, how long you've homeschooled, what you've learned, why you want to help others.

- Write down 3 specific problems you can solve for other homeschool moms.

Why this matters:

Every piece of your website, Facebook page, and pitch comes from this. Do not skip it.

DAY 2 — Set Up Your Free Business Tools

What to do:

- Create a free Gmail for the business — example: yourbusinessname@gmail.com

- Sign up for Calendly (free plan at calendly.com) using that email.

- Sign up for Stripe (free at stripe.com) — connect your bank account. This is how clients pay you.

- Sign up for Zoom (free plan) — this is where you run the calls.

Calendly setup (important):

- Create two event types: (1) "Free Discovery Call" — 15 minutes. (2) "Homeschool Consultation" — 25 minutes, price $50.

- Connect Calendly to Stripe so the $50 is collected automatically when someone books.

- Test it: book a fake appointment yourself to make sure payment works.

DAY 3 — Set Up Your Facebook Business Page

What to do:

- Go to facebook.com/pages/create and create a Business Page (not a personal profile).

- Page name: Your name or business name — something with "Homeschool" in it.

- Category: Education, Tutoring, or Consulting.

- Profile photo: A clear, friendly photo of yourself. No selfies with bad lighting.

- Cover photo: A simple image with your tagline (use Canva.com — free).

- Fill in the About section with your "I help" statement from Day 1.

- Add your Calendly booking link to the page as the contact/website link.

Your first post:

"Hey! I'm [name] and I've been homeschooling for [X years]. I just launched my consulting page to help other homeschool moms who feel lost or overwhelmed. I'm offering free 15-minute discovery calls this month — drop a comment or DM me if you want to chat."

DAY 4 — Join Homeschool Facebook Groups

What to do:

- Search Facebook for homeschool groups. Join at least 5. Mix of local (your city/state) and national.

- Search terms: "homeschool moms [your state]", "homeschooling support group", "homeschool curriculum help"

- Read the group rules before posting — many groups don't allow promo posts.

- Do NOT post your offer today. Just join, read, and observe what questions people ask. These are your future clients' pain points.

- Write down the top 3 questions or struggles you see people posting about.

DAY 5 — Create Your Content Plan

What to do:

- Based on what you saw in the groups on Day 4, write 5 short tips or answers to common questions.

- These become your first 5 Facebook posts (one per day in Week 2).

Example post format:

"One thing I wish I knew when I started homeschooling: [tip]. Have a question about this? Book a free 15-min call with me — link in bio."

- Keep posts under 150 words. Short, helpful, ends with a soft call-to-action.

DAY 6 — Ask Your Network

What to do:

- Message 10 people you know personally — friends, family, church members, neighbors.

- Tell them what you're doing and ask them to share your Facebook page.

- Script: "Hey [name], I just started a homeschool consulting business to help moms who feel overwhelmed getting started. Would you mind sharing my Facebook page? It would mean a lot. [page link]"

- This is not selling. This is planting seeds. Do not skip this step.

DAY 7 — Review + Rest

Checklist — confirm all of these are done:

- Gmail created

- Calendly set up with two booking types

- Stripe connected and tested

- Facebook Business Page live

- 5 posts drafted and ready

- 10 people messaged to share your page

- Website handed off to developer (see Part 2)

## WEEK 2 — Get Your First Clients (Days 8–14)

This week you shift from setting up to actively reaching out. Your goal is to book at least 3 free discovery calls — which convert to paid clients.

DAY 8 — Post Your First Value Post + Start Outreach

- Post Value Post #1 on your Facebook Business Page.

- Share your page on your personal Facebook profile.

- Go into each of your 5 homeschool groups. Find someone asking a question you can genuinely help with. Answer helpfully in the comments — do not mention your business yet. Just help.

- Do this every day this week. Helping first builds trust.

DAY 9 — Direct Outreach — DMs

- Find 10 people in your groups who are clearly struggling (posting questions, saying they're overwhelmed, etc.).

- Send them a friendly DM. Do NOT paste a promo message.

Script:

"Hey [name], I saw your post about [topic] — I totally get that struggle! I've been homeschooling for [X years] and actually just started consulting to help moms like you. I offer a free 15-minute call if you ever want to just talk it through. No pressure at all — just here if it helps!"

- Send 10 DMs. You will get 2–3 responses. That is normal.

DAY 10 — Post + Follow Up

- Post Value Post #2.

- Follow up with anyone who responded to your DMs yesterday — send your Calendly link.

- Answer more comments in the groups (genuine help, no promo).

DAY 11 — Post + Ask for Referrals

- Post Value Post #3.

- Follow up with the 10 people you messaged on Day 6 (the ones you asked to share). Thank whoever shared and ask if they know anyone who might need help.

- Send 5 more DMs in groups.

DAY 12 — Run Your First Discovery Call

If someone booked a free call, today is the day. Here is how to run it:

- Ask: "What's the biggest challenge you're facing with homeschooling right now?"

- Listen more than you talk. Take notes.

- Share 1–2 things that could help them.

- At the end: "I offer a 25-minute deep-dive session for $50 where we make an actual plan for your situation. Would that be helpful?"

- If yes: send them the Calendly paid link.

Do not overthink this. You are just having a conversation.

DAY 13 — Post + Website Review

- Post Value Post #4.

- Check with your developer — is the website live or almost ready?

- Review it on your phone — most of your clients will visit on mobile.

- Test the booking link on the website. Make sure it works.

- Send 5 more DMs.

DAY 14 — Final Review + Next Steps

- Post Value Post #5.

- Count: How many discovery calls booked? How many paid consultations?

- If 0 paid clients: That is okay. Send 10 more DMs today. The gap is always outreach volume.

- If 1–3 paid clients: You have validated the business. Keep posting, keep doing outreach.

- After Day 14: Raise your rate to $75 after your first 5 paid sessions and you have testimonials.

THE RULE: Outreach before content. A post on Facebook does nothing if nobody sees it yet. Every day, send at least 5 DMs. That is what gets you clients in the first 2 weeks, not a perfect website.

# PART 2: WEBSITE SPECIFICATION

This section is for the web developer. It covers every page, every piece of copy, and every tool that needs to be connected. Build exactly what is listed here — nothing more, nothing less.

## Overview

| Platform | Squarespace (recommended) or Wix — either works. Squarespace has cleaner templates for service businesses. |
| --- | --- |
| Number of pages | 4 pages total |
| Domain | Buy from Squarespace or Namecheap. Something like [name]homeschoolconsulting.com or homeschoolwith[name].com |
| Scheduling | Calendly (free plan) — embedded on Booking page |
| Payments | Stripe — connected to Calendly for paid sessions |
| Video calls | Zoom or Google Meet — auto-sent by Calendly after booking |
| Email shown | Business Gmail created in Day 2 |
| Mobile | Must look good on phones — most visitors will be on mobile |

## Page 1 — Home

Purpose:

Tell visitors exactly who you help and what you do within 5 seconds of landing.

Sections to build:

- HERO (top of page): Large headline. Use their "I help" statement from Day 1. Sub-headline: 1 sentence about how. Button: "Book a Free Call" linking to the booking page.

- HOW IT WORKS: 3 steps with icons. Step 1: Book a free 15-min discovery call. Step 2: We talk through your situation. Step 3: You get a clear plan and next steps.

- WHO THIS IS FOR: A short paragraph or 3-bullet list of the types of moms they help (new homeschoolers, overwhelmed moms, moms switching from public school, etc.).

- SOCIAL PROOF (placeholder): Add a section for testimonials. Leave it empty for now or use a placeholder like "Reviews coming soon." Once they have clients, fill this in.

- FINAL CTA: Another button at the bottom — "Ready to get started? Book your free call."

## Page 2 — About

Purpose:

Build trust. People hire people, not services. This page makes them feel like they know her.

Sections to build:

- Photo: A clear, warm photo. Natural lighting. Smiling. Not a corporate headshot.

- Her story: Use the bio written on Day 1. Expand it slightly — how long she's been homeschooling, what her own kids' experience has been, what she learned the hard way.

- Why she helps: A short paragraph on why she started consulting.

- A few personal details (optional): Makes her feel real — hobbies, faith, family, etc.

- CTA at the bottom: "Want to work together? Book a free call."

## Page 3 — Services

Purpose:

Show exactly what is offered and how much it costs. Be clear. No confusion.

Service 1 — Free Discovery Call

| Price | Free |
| --- | --- |
| Length | 15 minutes |
| Format | Video call (Zoom or Google Meet) |
| Who it's for | Anyone new or unsure — no commitment required |
| What happens | Quick conversation to understand your situation and see if consulting is a good fit |
| Button | "Book Your Free Call" → links to Calendly free event |

Service 2 — Homeschool Consultation

| Price | $50 |
| --- | --- |
| Length | 25 minutes |
| Format | Video call (Zoom or Google Meet) |
| Who it's for | Moms ready to get real help and a specific plan |
| What's covered | Curriculum selection, scheduling, learning styles, getting started, troubleshooting |
| What you get | A clear action plan and next steps you can start immediately |
| Button | "Book a Consultation — $50" → links to Calendly paid event with Stripe |

## Page 4 — Book a Call

Purpose:

One job only: get the visitor to book. Keep this page simple.

Sections to build:

- Short headline: "Ready to get started? Pick a time below."

- 1–2 sentence reminder of what they get: "Choose your free discovery call or a paid consultation. Both happen over video call — no travel, no hassle."

- Embed the Calendly widget directly on this page (Calendly provides an embed code). The widget should show both booking options.

- Nothing else on this page. No distractions. Just the booking widget.

## Technical Checklist for the Developer

| Task | Done? |
| --- | --- |
| Domain purchased and connected | [ ] |
| 4 pages created: Home, About, Services, Book a Call | [ ] |
| Calendly widget embedded on Book a Call page | [ ] |
| All CTA buttons link to correct Calendly event (free vs. paid) | [ ] |
| Stripe connected to Calendly paid event — test transaction verified | [ ] |
| Business Gmail added to contact/footer | [ ] |
| Site looks good on mobile (check on an actual phone) | [ ] |
| Facebook page linked in site footer | [ ] |
| Page load speed acceptable (no uncompressed huge images) | [ ] |
| Site published — not left in draft mode | [ ] |

SCOPE NOTE FOR DEVELOPER: The above is everything included in this project. Any additions beyond these 4 pages, the Calendly/Stripe integration, and mobile responsiveness should be quoted and agreed to separately.

# QUICK REFERENCE — Tools & Costs

| Tool | Cost | What it does |
| --- | --- | --- |
| Gmail | Free | Business email address |
| Calendly | Free | Booking link for both call types |
| Stripe | Free to sign up (2.9% + 30¢ per transaction) | Takes payment when clients book |
| Zoom | Free (40-min limit) | Video calls |
| Squarespace | ~$16/month | Website builder (includes domain) |
| Canva | Free | Design profile/cover photos |
| Facebook Page | Free | Social media presence |

Follow the plan. Do the outreach. The website is just a tool — clients come from conversations.

MY DAY 1 ANSWERS

My "I help" statement:

"I help new and overwhelmed homeschool moms who don't know where to start build a simple, effective homeschool routine their kids actually enjoy."

Short bio:

(To be filled in)

3 problems I can solve for homeschool moms:

1. (To be filled in)

2. (To be filled in)

3. (To be filled in)